## POA&M Working List
WUC | NSN | Noun | Current Unofficial Ranking (Awaiting SPO Validation) | Rank May 2021 Used to Update KC-135 Parts Tracker | Rank Dec 2020 Used to Develop Skittle Chart | Currently Fielded CBM+ | Need to Conduct Constraint Analyses | Components going forward on POA&Ms | Included in PAVCON RCA | Constraints & Action Plan From Aug-21 Mtg | Lead_Office | Lead_POC | POA&M Objective Narrative | T&R to Overhaul Milestones | Contract Language Milestones | Planned Modification Milestones | Supply Constraints Milestones | Reliability Milestones | POA&M Completion Date | SOR Specific Organic ALC Specific Contractor | Repair Concept | Contract Repair | USAF Repair Contract No. | DLA Contract No. | Contracting Officer | Contract notes | Award Date | Contract Expiration Date | Contracting Organization | PR Status | WSLO Notes | Repair Contractor | LMS | PMS | IM | ES | Constraints | Get Well Solution | Reliability | Test_and_Repair | Supply | Mod | TBD | Rating
51FB0 | 6610-99-732-8120 | INTEGRATED FUEL MANAGEMENT PANEL 57-001-0 | 10 | 1 | 2 | N |  | Y | Y | 51FB0 Plan | KC-135 SPO | Beth Hottle | Change Repair Concept from T&R to Overhaul | [6 empty] | BAE | T&R | Yes | FA811717D0015 | N/A | Kristen Carter | USAF Requirements contract / repair only |  | 2022-09-01 | PZABA Tinker Robin Adee's section | Initial CRTS Complete, IGE and SSS in work | Not recommended due to test stand upgrade and refresh ECD 2027. Currently, top 5 grounding MICAP driver. Don't want to delay contract award. WSLO will ask senior leaders during the next Way-Ahead meeting their input about CBM+ language. 1/4/22 - WSLO's talked with our leadership through the CBM+ Cell Team. Tracy has the update on their input. | Organic Test and minor repair at Hill AFB Major repair at BAE | james.heaton@us.af.mil |  | mikayla.kwitowski@us.af.mil | robert.smith.287@us.af.mil | Supply constraint root cause: Capacity/Capability Issues: (BAE) Ogden Organic shop can only do minor repair. In-depth repair contract with BAE; del sch. of 4ea/120days. Vendor has cited test equipment and obsolescence as sustainability issues. Engineering effort has been canceled. NSN will be replaced in 2027 (unfunded). Short term fix in work: None: RSO/PavCon initiate RCA to identify potential short term solutions Risks (threats): BAE willingness to negotiate Risk Mitigation Actions Gov Council discussion (for short term): - Tracy, Jeremy, Brandon, Dell Plan A 1. Go to BAE...use other BAE business as leverage to push BAE to fix this issue (upgrade test stand, INCREASE production, refresh the part, etc). - Tracy to ask "loggy" if SC has contacted BAE 1a. Modify existing contract - feasible due to timing? 1b. Add MDR reqts, minimum life / PBL, CBM+ language into Aug/Sep 2022 contract 2. Minor repair performed at Ogden currently...purchase data rights (negotiate) or collaborate with BAE to build USAF test stand and then have Ogden (or other) can do more repair organically? I have in notes that if BAE refuses the contract, then they must provide the data rights to the USAF...so why would we purchase them? 3. Secure and protect the funding for Long term CCR mod. Long term Fix: Part of Center Console Refresh (CCR) modification NOT FUNDED (est 2027/2028). Risks (threats) for long term: Funding Loss | Plan of Action Short Term: - Option 1: Modify current contract to update test stand and meet AF MDR - Option 2: Add test stand update, CBM+ language, and PBL into 2022 contract - Option 3: If BAE refuses to bid, BAE must provide data rights to the AF who will stand up organic capability Long Term: Center console refresh (CCR) planned for 2027+ is unfunded |  |  |  | x
729QC | 6610-01-501-3600 | COMMON COMPUTING MODULE (W) | 11 | 2 | 1 | N |  | Y | N | 729QC Plan | KC-135 SPO | Beth Hottle | [7 empty] | Rockwell Collins | T&R | Yes | FA8117-17-D-0018 | SPE4X21D9400KO SPE4AX21D9400 (REPAIR AND SPARES) | DLA (SPE4AX) not priced on this contract yet USAF (FA8117) Shelia Thee (PZABA Robin Adee's section) | SPE4AX21D9400 is a DLA corporate contract with Collins FA8117-17-D-0018 is a USAF requirements contract for repair |  | 2022-08-01 | PZABA Tinker Robin Adee's section | Initial CRTS Complete, IGE and SSS in work | Not recommended due to contractor performance and grounding MICAPs. Item is on the same contract with DTU | Collins Aero. | lana.alexander@us.af.mil | daniel.dugan@us.af.mil | nicholas.nguyen.8@us.af.mil | jeffrey.price.8@us.af.mil | Supply constraint root cause = Contractor performance Carcass short Short term fix in work: (Collins Aero.) Shared test stand. Contractor working to increase output to 25-35ea/month to reduce backlog. Contract modification to add 501 P/N was completed on 6 Jan 21. Up the MDR. Risks (threats): CSAG funding loss, No data rights (vendor), lack of carcasses, costs associated with contract mods, ownership (gov versus vendor) of test stand will impact costs Risk Mitigation Actions Gov Council discussion (for short term): 1. Up the production (contract specified) on the current contract? - Tracy Leads 2. Field Repair option? (Collins reps at the base??) 3. Purchase Test stand place at USAF installation (TBD)? - Beth Leads 3.1 Setup repair site? - Supply Chain (TBD) 4. Consider existing test stand locations to work these? 5. New data set to be analyzed - Mary B | Long term Fix: Refresh 2024/2025 Choice #1 This item will be used as a pilot to add reliability language to the contract...utlize C130 as baseline. Short Term: Add CBM+ language into the sustainment contract (current contract ends August 2022); adjust contract to meet MDR; establish performance-based logistics (PBL) construct - Option 1: Collins meets new contract requirements; AF incentivizes Collins to increase time on wing (TOW) reliability - Option 2: Collins rejects contract and AF established I-level capability Long Term: 2025 refresh; consider field-level repair of refresh part |  |  |  | x
51JA0 | 5841-01-504-5586 | MULTIFUNCTION DISPLAY MFD-255K | 12 | 5 | 4 | N |  | Y | Y | 51JA0 Plan | KC-135 SPO | Beth Hottle | [7 empty] | Rockwell Collins | T&R | Yes | SPE4AX21D9400 | SPE4X21D9400KO SPE4AX21D9400 | DLA (SPE4AX) | DLA Corporate |  | 2030-10-01 | DLA (SPE4AX) | NA | Not recommended due to current repair contract expiration date is over 5 years or more. CORP CONTRACT | Rockwell Collins | anthony.simmons@us.af.mil | Jason.massengale@us.af.mil | shelda.cenat.1@us.af.mil | james.baker.74@us.af.mil | Supply constraint root cause: Contractor Performance Short term fix in work: (CollinsAero.) Constrained by no SOS for LCD Glass; new glass was approved. PR qty194 for adding LCD Glass and Graphics Cards. Lack of funding for DOR delayed repair. Awarded 23 Jul 21. SOH at Contractor. 45 days After Receipt Order. - Get well date January 2022...supply chain - RSO/PavCon initiate RCA to identify potential short term solutions - This part is a Top priority for 448th study due to impact on fleet Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): none Long term Fix: Refresh 2027/2028 NOT FUNDED Risk Mitigation Action for Gov Council discussion (long term): 1. Secure and protect funding for Modification (CCR modification) | Long term Fix: Refresh 2027/2028 NOT FUNDED Risk Mitigation Action for Gov Council discussion (long term): 1. Secure and protect funding for Modification (CCR modification) | x |  |  | x |  | x
729QB | '6610-01-502-0350 | INPUT OUTPUT CONCENTRATOR (W) | 13 | 4 | 3 | N |  | Y | N | 729QB Plan | KC-135 SPO | Beth Hottle | [7 empty] | Rockwell Collins | T&R | Yes | FA8117-18-D-0002 | SPE4X21D9400KO SPE4AX21D9400 | DLA (SPE4AX) not priced on this contract yet USAF (FA8117) Shelia Thee (PZABA Robin Adee's section) | SPE4AX21D9400 is a DLA corporate contract with Collins for repair and spares FA8117-18-D-0002 is a USAF requirements contract for repair |  | 2022-11-01 | PZABA Tinker Robin Adee's section | Initial CRTS Complete, IGE and SSS in work | Not recommended due to contractor performance and grounding MICAPs | Rockwell Collins | lana.alexander@us.af.mil | daniel.dugan@us.af.mil | Nicholas.nguyen.8@us.af.mil | jeffrey.price.8@us.af.mil | SAME AS CCM Supply constraint root cause = Contractor performance Carcass short Short term fix in work: (Rockwell Collins) Shared test stand. Contractor working to increase output to 25-35ea/month to reduce backlog. Currently 40 failing in field monthly. Contract modification to add 501 P/N was completed on 6 Jan 21. Up the MDR. Contract expires August 2022. CBM+ language needs adding to contract. Risks (threats): CSAG funding loss, No data rights (vendor), lack of carcasses, costs associated with contract mods, ownership (gov versus vendor) of test stand will impact costs Risk Mitigation Actions Gov Council discussion (for short term): Plan A 1. Incentivize Collins to increase TOW (reliability clause / PBL contract) and Collins must meet changing demand requirements / minimum MDR - Tracy Leads Plan B 2. If Collins refuses contract requirements, AF establishes I-level capability (Collins reps at the base? Collins owns tech data.) Would require purchase of test stand at USAF installation. - Beth leads 2a. Setup repair site? - Supply Chain (TBD) 2b. Consider existing test stand locations to work these? New data set to be analyzed in support of Plans A and B Long term Fix: Refresh 2024/2025 Choice #1 This item will be used as a pilot to add reliability language to the contract...utlize C130 as baseline. | Plan of Action Short Term: Add CBM+ language into the sustainment contract (current contract ends August 2022); adjust contract to meet MDR; establish performance-based logistics (PBL) construct â€¢ Option 1: Collins meets new contract requirements; AF incentivizes Collins to increase time on wing (TOW) reliability â€¢ Option 2: Collins rejects contract and AF established I-level capability Long Term: 2025 refresh; consider field-level repair of refresh part | x | x |  | x |  | x
73AA0 | 5841-01-470-8036 | E-TCAS PROCESSOR (TPS-81A) | 15 | 8 | 11 | N |  | Y | Y | E-TCAS 73AA0 Plan | KC-135 SPO | Beth Hottle | [7 empty] | Honeywell | T&R | Yes | FA853918D0001 | N/A | Antwan T. Thomas | USAF requirements contract for repair |  | 2022-12-01 | Robins AFB - PZABA | Gate 1 (RFI posted, market research report is being fine-tuned, and PM is working on SASS) | WSLO emailed PM to ask about AAC V status; and if PR is with SC, PR Cell or Contracting. SC is working on follow on PR FD2060220023; EAD 30 Sep 22 | N/A Honeywell contractor repair | allan.pratt.1@us.af.mil | Loretta.lindley@us.af.mil | shelda.cenat.1@us.af.mil | james.baker.74@us.af.mil | Supply constraint root cause: b. Undergoing additional modification c. No current supply constraint analysis being performed Risks (threats): NA Risk Mitigation Actions Gov Council discussion (for short term): NA Risk Mitigation Action for Gov Council discussion (long term): NA | Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Undergoing additional modification. Consider purchase new version NSN: 5841-01-641-1494 versus old version. ACTION: Jeremy/SPO RCA - determine cost benefit of new versus repair. Determine if other airframes are experiencing issues? Long term: ACTION SPO: Discuss with Honeywell...need long term repair/sustainment plan. | x | x |  |  |  | x
713A0 | 5895-01-500-7538 | MULTI-MODE RECEIVER (MMR) (W) | 20 | 6 | 8 | N |  | Y | Y | 713A0 Plan | KC-135 SPO | Beth Hottle | [7 empty] | Collins (Aero) | T&R | Yes | FA8117-18-D-0006 | N/A | Shelia Thee | FA8117-18-D-0006 is a USAF requirements contract for repair |  | 2022-12-01 | PZABA Tinker Robin Adee's section | Initial CRTS Complete, IGE and SSS in work | Not recommended due current constraints and increasing grounding MICAP hours on the MMR. | Collins | jeremy.munoz@us.af.mil | Christi.berry@us.af.mil | velma.campbell@us.af.mil | steven.ramirez@us.af.mil | Supply constraint root cause: Contractor Performance (Collins Aerospace) Contractor has one test stand and limited personnel that runs tester; discussions with contractor resulted in push for production of 16/month Part Health: 66BOs no MICAPs ACTION Dewayne - see if mod package is in work to address this. Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Not at this time Risk Mitigation Action for Gov Council discussion (long term): Not at this time | Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Discussions with contractor resulted in push for production of 16/month TO change published, TCTO released. Obsolescence issues with current. Action Jeremy - Need newer data to perform RCA and verify TO change Long term - Collins identified a new part to replace this one. Is this FFF vs Mod. Potential IIRP "bucket". Action DeWayne - work with SPO engineering to determine how quickly the new mod with updated GPS will be implemented. NOTE: potential candidate for overhaul process organic or vendor versus current test and repair process | x |  | x |  |  | x
51FA0 | 6610-01-435-2935 | FMAC, 490200-05-01 (W) | 21 | 22 | 52 | N |  | Y | Y | 51FA0 Plan | KC-135 SPO | Beth Hottle | [7 empty] | BAE | T&R Minor at OO-ALC Major at BAE | Yes | FA811717D0015 | N/A | Kristen Carter | USAF Requirements contract / repair only |  | 2022-09-01 | PZABA Tinker Robin Adee's section | Initial CRTs complete. IGE and SSS in work. New PR FD20302102631; EAD Sep 22 | Not recommended due to item on the same contract with IMFP, which requires a test stand upgrade. | BAE Systems | james.heaton@us.af.mil |  | tiffany.sebring@us.af.mil | robert.smith.287@us.af.mil | Center Console Refresh NOT Funded | AVIP 8: 17 APRIL 2017: With a new IFMP, the FMAC will be removed from the aircraft. Recommend Closing Get Well Dates JCS/700: Now, MICAP: Now, Priority: 10/07/2022, Routine: 03/17/2023, POC: Mike Heaton, Routing Symbol: 422 SCMS/GUMC, DSN: 884-7458 | x | x |  | x |  | x
51LAA | 6610-01-462-5980 | FLIGHT DATA RECORDER/COCKPIT VOICE RECORDE | 24 | 18 | 16 | N |  | Y | Y | 51LAA Plan | AFSC/LZRB | Del Hodge | [7 empty] | GE Aviation | T&R | Yes | FA811720D0031 | N/A | Robin Adee |  | 2020-09-01 | 2025-09-01 | PZABA Tinker Robin Adee's section | NA | Not recommended due to current repair contract expiration date is over 5 years or more. | GE Aviation | mariah.schon.1@us.af.mil | robert.masoner@us.af.mil | steven.headlee@us.af.mil | robert.smith.287@us.af.mil | Supply constraint root cause: Contractor Performance GE Aviation Several Over & Above requests on previous repair contract impacted production due to long lead time. Follow-on repair contract awarded Sep 20; includes major and minor repair to eliminate this in the future. Delivery Schedule: Major Repair 5ea/90days and Minor Repairs 15ea/45days Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Hold until we hear from AMC Risk Mitigation Action for Gov Council discussion (long term): Hold until we hear from AMC | Get well Date: December 2021 Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Isn't IIRP a long term solution? If yes, move all below to long term fix. Assume IIRP takes years. Also, I thought the new FDR was already approved and in procurement with 2024 install date?? IIRP Package is with 422th that is reviewing. ACTION: Dave H to talk to POC at AMC A5/8 who declined package...Tracy will get the POC name to Dave H/Lt Col Scozzaro
728C0 | 5841-01-432-3798 | RECEIVER TRANSMITTER WRT-701X | 27 | 16 | 14 | N |  | Y | Y | 728C0 Plan | AFSC/LZRB | Del Hodge | [7 empty] | Rockwell Collins | T&R | Yes | SPE4AX21D9400 | SPE4X21D9400KO SPE4AX21D9400 | DLA (SPE4AX) | DLA Corporate |  | 2030-10-01 | DLA (SPE4AX) | NA | Not recommended due to current repair contract expiration date is over 5 years or more. SC already pursued modifying the newly awarded contract to add CBM+ language; and received no response. CORP CONTRACT | Rockwell Collins | anthony.simmons.12@us.af.mil | Jason.massengale@us.af.mil | shelda.cenat.1@us.af.mil | james.baker.74@us.af.mil | Loss of weather awareness. AVIP 17: The WXR-700X is a commercial off-the-shelf color weather Radar system provided by Rockwell Collins. There was a lapse in the repair contract which led to a lot of aircraft canns in the field and high NMCS numbers. The IM has been contacted and there is funding in FY15 to repair assets. RC working Whitepaper on alternatives available for this item. ECD April 2018.. MH=1968; Demands=179; UC=$8,104 | Spiral 2 comp; Ctr; Test and Repair; Contract expired Fall 2020 - no CBM+ language added; potential contract mod (T. Miles action) | x |  |  |  |  | x
27CBA | 2995-01-140-2105 | STARTER | 28 | 26 | 18 | N |  | Y | Y | 27CBA Plan | AFSC/LZRB | Del Hodge | [7 empty] | OO-ALC | Overhaull | No |  | x | x |  |  |  | x
72HA0 | 6605-01-426-8522 | EMBEDDED GPS INS (EGI) 5-Channel Unit | 30 | 19 | 21 | N |  | Y | Y | 72HA0 | AFSC/LZRB | Del Hodge | [7 empty] | Honeywell | T&R | Yes | FA8576-20-D-0001 | N/A | Todd M. Rissmiller | USAF Enterprise IDIQ |  | 2029-12-01 | Robins AFB - WKNF | NA | Not recommended due to current repair contract expiration date is over 5 years or more. | Honeywell |  |  | robert.stringer@us.af.mil | anthony.shurley@us.af.mil | Supply constraint root cause: Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): | Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Risks (threats):
13CBM | 1650-00-877-6095 | RES BRK ACCUMULATOR | 35 | 33 | 26 | N |  | Y | Y | 13CBM Plan | DLA | Rob Williams | [7 empty] | Field Level (XF3) | ? | No

## Sheet2
WUC | NSN | WUC Name | POA&M Objective Narrative | POA&M Completion Date
51FB0 | 6610-99-732-8120 | INTEGRATED FUEL MANAGEMENT PANEL 57-001-0 | Change Repair Concept from T&R to Overhaul
729QC | 6610-01-501-3600 | COMMON COMPUTING MODULE (W)
51JA0 | 5841-01-504-5586 | MULTIFUNCTION DISPLAY MFD-255K
729QB | '6610-01-502-0350 | INPUT OUTPUT CONCENTRATOR (W)
73AA0 | 5841-01-470-8036 | E-TCAS PROCESSOR (TPS-81A)
713A0 | 5895-01-500-7538 | MULTI-MODE RECEIVER (MMR) (W)
51FA0 | 6610-01-435-2935 | FMAC, 490200-05-01 (W)
51LAA | 6610-01-462-5980 | FLIGHT DATA RECORDER/COCKPIT VOICE RECORDE
728C0 | 5841-01-432-3798 | RECEIVER TRANSMITTER WRT-701X
27CBA | 2995-01-140-2105 | STARTER
72HA0 | 6605-01-426-8522 | EMBEDDED GPS INS (EGI) 5-Channel Unit
13CBM | 1650-00-877-6095 | RES BRK ACCUMULATOR

## Supply
WUC | NSN | WUC Name | Constraint_Root_Cause | Issue | Risks | Risk_Mitigation | Plans | Plan B
51FB0 | 6610-99-732-8120 | INTEGRATED FUEL MANAGEMENT PANEL 57-001-0 | Contractor performance - Capacity/Capability | Ogden Organic shop can only do minor repair. In-depth repair contract with BAE; del sch. of 4ea/120days. Vendor has cited test equipment and obsolescence as sustainability issues. Engineering effort has been canceled. NSN will be replaced in 2027 (unfunded). | BAE willingness to negotiate |  | Go to BAE...use other BAE business as leverage to push BAE to fix this issue (upgrade test stand, INCREASE production, refresh the part, etc). - Tracy to ask "loggy" if SC has contacted BAE a. Modify existing contract - feasible due to timing? b. Add MDR reqts, minimum life / PBL, CBM+ language into Aug/Sep 2022 contract 2. Minor repair performed at Ogden currently...purchase data rights (negotiate) or collaborate with BAE to build USAF test stand and then have Ogden (or other) can do more repair organically? I have in notes that if BAE refuses the contract, then they must provide the data rights to the USAF...so why would we purchase them? 3. Secure and protect the funding for Long term CCR mod. Long term Fix: Part of Center Console Refresh (CCR) modification NOT FUNDED (est 2027/2028).
729QC | 6610-01-501-3600 | COMMON COMPUTING MODULE (W) | Contractor performance - Carcass short |  |  |  |  | 3. Secure and protect the funding for Long term CCR mod.
51JA0 | 5841-01-504-5586 | MULTIFUNCTION DISPLAY MFD-255K | [5 empty] | Long term Fix: Part of Center Console Refresh (CCR) modification NOT FUNDED (est 2027/2028).
729QB | '6610-01-502-0350 | INPUT OUTPUT CONCENTRATOR (W) | [5 empty] | Risks (threats) for long term: Funding Loss
73AA0 | 5841-01-470-8036 | E-TCAS PROCESSOR (TPS-81A)
713A0 | 5895-01-500-7538 | MULTI-MODE RECEIVER (MMR) (W)
51FA0 | 6610-01-435-2935 | FMAC, 490200-05-01 (W)
51LAA | 6610-01-462-5980 | FLIGHT DATA RECORDER/COCKPIT VOICE RECORDE
728C0 | 5841-01-432-3798 | RECEIVER TRANSMITTER WRT-701X
27CBA | 2995-01-140-2105 | STARTER
72HA0 | 6605-01-426-8522 | EMBEDDED GPS INS (EGI) 5-Channel Unit
13CBM | 1650-00-877-6095 | RES BRK ACCUMULATOR

## 1-N List
WUC | NSN | WUC Name | Current Unofficial Ranking (Awaiting SPO Validation) | Rank May 2021 Used to Update KC-135 Parts Tracker | Rank Dec 2020 Used to Develop Skittle Chart | Currently Fielded CBM+ | Need to Conduct Constraint Analyses | Components going forward on POA&Ms | Included in PAVCON RCA | Constraints & Action Plan From Aug-21 Mtg | Lead Action Plan Office | POC Leading Action Plan | Notes | SOR Specific Organic ALC Specific Contractor | Repair Concept | Contract Repair | Reliability | T&R | Supply | Mod | TBD | Rating
45175 | 4320-00-768-6345HS | AUX HYD PUMP | 1 | NA | NA | Y |  | N | [5 empty] | OO-ALC
42310 | 1650-01-141-6018 | INTEGRATED DRIV GEN | 2 | NA | NA |  | Y |  |  |  |  | TBD | First time on 1-N List need to conduct a Root Cause Analyses to determine if there's any current constraints
52210 | 6615-01-138-2369 | COMPUTER FLIGHT CONTROL | 3 | 24 | 22 |  | Y |  |  | See Watch List Need to Conduct a Constraints Analyses |  | TBD |  | OC-ALC
46750 | 001095725 001095730 | BOOM ASSEMBLY | 4 | 20 | 42 |  |  | N |  | 46750 Plan |  | TBD |  | OC-ALC
51114 | 6610-01-452-2715 | STANDBY ATTITUDE DIRECTION INDICATOR (SADI) | 5 | NA | NA |  | Y |  |  |  |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist
51612 | 6680-00-726-9826 | TRANSMITTER LH | 6 | NA | NA |  | Y |  |  |  |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist
46771 | 1680-00-656-6170 | NOZZLE ASSY | 7 | NA | NA |  | Y |  |  |  |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist
47131 | 4730-00-278-9126 | OXYGEN REG | 8 | NA | NA |  | Y |  |  |  |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist
41126 | 1660-01-290-2065 | CABIN PRES CNTL | 9 | 32 | 24 | Y |  | N |  | 41126 Plan |  |  | Currently fielded | OC-ALC |  |  | x |  |  |  |  | x
51FB0 | 6610-99-732-8120 | INTEGRATED FUEL MANAGEMENT PANEL 57-001-0 | 10 | 1 | 2 |  |  | Y | Y | 51FB0 Plan | KC-135 SPO | Beth Hottle |  | BAE | T&R | Yes | x | x |  | x |  | x
729QC | 6610-01-501-3600 | COMMON COMPUTING MODULE (W) | 11 | 2 | 1 |  |  | Y |  | 729QC Plan | KC-135 SPO | Beth Hottle | Part of 729Q0 | Rockwell Collins | T&R | Yes | x | x |  | x |  | x
51JA0 | 5841-01-504-5586 | MULTIFUNCTION DISPLAY MFD-255K | 12 | 5 | 4 |  |  | Y | Y | 51JA0 Plan | KC-135 SPO | Beth Hottle |  | Rockwell Collins | T&R | Yes | x |  | x | x |  | x
729QB | '6610-01-502-0350 | INPUT OUTPUT CONCENTRATOR (W) | 13 | 4 | 3 |  |  | Y |  | 729QB Plan | KC-135 SPO | Beth Hottle |  | Rockwell Collins | T&R | Yes | x | x |  | x |  | x
46766 | 002499370 016506340 | RUDDEVATOR | 14 | 27 | 33 |  |  |  |  | See Watch List |  | TBD | Supply constraint root cause: Carcass constraints, backshop workflow constraints | OC-ALC
73AA0 | 5841-01-470-8036 | E-TCAS PROCESSOR (TPS-81A) | 15 | 8 | 11 |  |  | Y | Y | E-TCAS 73AA0 Plan | KC-135 SPO | Beth Hottle |  | Honeywell | T&R | Yes | x |  |  | x |  | x
27HAJ | 12865565 | POWER MANAGEMENT CONTROL | 16 | 42 | 20 |  | Y | N |  | See Watch List |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist |  |  | Yes | x | x |  |  |  | x
11447 | 015033310 005756494 | BOOM SIGHTING DOOR WINDOW | 17 | NA | NA |  | Y |  |  |  |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist
46717 | 996418724 | MANIFOLD VALVE | 18 | NA | NA |  | Y |  |  |  |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist
4511P | 4230012425153 4320011653532 | HYD PUMP F108-CF-100 | 19 | NA | NA | Y |  | N |  | Possible RCA required |  |  | Currently fielded | OO-ALC
713A0 | 5895-01-500-7538 | MULTI-MODE RECEIVER (MMR) (W) | 20 | 6 | 8 |  |  | Y | Y | 713A0 Plan | KC-135 SPO | Beth Hottle |  | Collins (Aero) | T&R | Yes | x |  |  | x |  | x
51FA0 | 6610-01-435-2935 | FMAC, 490200-05-01 (W) | 21 | 22 | 52 |  |  | Y | Y | 51FA0 Plan | KC-135 SPO | Beth Hottle |  | BAE | T&R Minor at OO-ALC Major at BAE | Yes |  | x
45161 | 1650-00-877-6095 1650-00-640-8489 | ACCUMULATOR | 22 | NA | NA | Y |  | N |  | Possible RCA required |  |  | Currently fielded | OO-ALC
51156 | 6610-01-115-3518 | PITOT TUBE | 23 | NA | NA |  | Y |  |  |  |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist
51LAA | 6610-01-462-5980 | FLIGHT DATA RECORDER/COCKPIT VOICE RECORDE | 24 | 18 | 16 |  |  | Y | Y | 51LAA Plan | AFSC/LZRB | Del Hodge |  | GE Aviation | T&R | Yes | x | x |  |  |  | x
5131J | 6685-01-162-4291 | INDICATOR EGT | 25 | NA | NA |  | Y |  |  |  |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist
42330 | 6110-01-141-4879 | CONT UNIT GENERATOR | 26 | NA | NA |  | Y |  |  |  |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist
728C0 | 5841-01-432-3798 | RECEIVER TRANSMITTER WRT-701X | 27 | 16 | 14 |  |  | Y | Y | 728C0 Plan | AFSC/LZRB | Del Hodge |  | Rockwell Collins | T&R | Yes | x | x |  |  |  | x
27CBA | 2995-01-140-2105 | STARTER | 28 | 26 | 18 |  |  | Y | Y | 27CBA Plan | AFSC/LZRB | Del Hodge |  | OO-ALC | Overhaull | No | x |  | x |  |  | x
5131G | 6620-00-003-9771 | FUEL FLOW INDICATOR | 29 | NA | NA |  | Y |  |  |  |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist
72HA0 | 6605-01-426-8522 | EMBEDDED GPS INS (EGI) 5-Channel Unit | 30 | 19 | 21 |  |  | Y | Y | 72HA0 | AFSC/LZRB | Del Hodge | Part of 72H00 | Honeywell | T&R | Yes | x | x |  |  |  | x
13AHF | 1650-01-582-2429 | CENTERING CYLINDER | 32 | 11 | 13 |  | Y |  |  | See Watch List | AFSC/LZRB | Del Hodge | Need to verify constraint | OO-ALC | Overhaull | No |  |  |  | x |  | x
13CBM | 1650-00-877-6095 | RES BRK ACCUMULATOR | 35 | 33 | 26 |  |  | Y | Y | 13CBM Plan | DLA | Rob Williams | DLA XF3 Asset | Field Level (XF3) | ? | No | x |  |  |  |  | x
65DAA | 5841-01-556-3173 | MODE SLIFF TRANSPONDER RT-1861 (PN4079100 | 41 | 35 | 25 |  | Y |  |  | See Watch List |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist |  |  | Yes | x | x |  |  |  | x
729K0 | 7025-01-525-6110 | DATA TRANSFER UNIT DTU-7000 (W) | 48 | 17 | 12 |  | Y |  |  | See Watch List |  | TBD | Need to conduct a Constraints Analyses to determine if any current constraints exist |  |  | Yes | x | x |  |  |  | x
729B0 | 6610-01-444-0953 | CONTROL DISPLAY UNIT DCU-900B | 31 |  |  |  | Y |  |  |  |  | KC-135 SPO (Ms. Hottle) | Need to conduct a Constraints Analyses to determine if any current constraints exist |  |  | Yes
51EF0 | NEED NSN | TANK INTERFACE UNIT | 249 |  |  |  | Y |  |  |  |  | KC-135 SPO (Ms. Hottle) | Need to conduct a Constraints Analyses to determine if any current constraints exist
45110 | NA - System | HYDRAULIC SYSTEM | NA | 3 | 23 |  |  |  |  | 45110 Plan |  | NA | 4511P fielded Assembly breakdown ID'ed 4511P HP (fielded Sp1); 4511T lines (not recommended, most sched mx); not analyzing 45110
729Q0 | N/A – Assembly/015019435 | INTEGRATED PROCESSING CENTER (W) | NA | 7 | 7 |  |  |  |  | 729Q0 |  | NA | 729QC and 729QA Breakdown ID'ed 729QC CCM, 729B0 (not LRU), 729QB IOC; two top are on 1-n |  |  | Yes
72800 | NA - Subsystem | WXR-700X COLOR WEATHER RADAR SYSTEM | NA | 9 | 5 |  |  |  |  | 72800 Plan |  | NA | 728C0 Breakdown ID'ed 728C0 (#14 on 1-n); potentially 728E0 radar control panel
41120 | NA - System | PRESSURIZATION | NA | 10 | 6 |  |  |  |  | 41120 Plan |  | NA | 41126 (Fielded) and 41123 (Fielded) Breakdown ID'ed 41123 OSV (fielded Sp1) and 41126 cabin P control (fielded Sp3)
72H00 | NA - System | EMBEDDED GPS INS (EGI) SYSTEM | NA | 12 | 10 |  |  |  |  | 72H00 |  | NA | 72HA0 Breakdown ID'ed 72HA0 EGI (#21 on 1-n), 72HH0 (discontinued), 72HM0 (#72 on 1-n)
13A00 | NA - System | MAIN LANDING GEAR SYSTEM | NA | 13 | 19 |  |  |  |  | See Watch List |  | NA | 13AHF Breakdown ID'ed 13AHF Ctr Cyl (Sp2 under mod, #13 on 1-n) - awaiting mod results; 13AM0 wheel tire (#53 on 1-n)
72900 | NA - System | FMS-800 FLIGHT MANAGEMENT SYSTEM | NA | 14 | 9 |  |  |  |  | 72900 Plan |  | NA | 729K0 Breakdown ID'ed CCM and IOC (Sp2 CLS T&R), 729B0 (#32 on 1-n), 729Q0 (#7 on 1-n); look at 72900 mx data to ID other comp. level R2
41210 | NA - System | CABIN AIR COND SYS | NA | 28 | 27 |  |  |  |  | 41210 Plan |  | NA | Need to find out what is going on with 4121F and 41214 Assembly breakdown identified 4121F Alt P and 41214 water separator; potential to consider 4121F Alt P/Aux Heat valve for analysis - NEED TEAM INPUT TO ANALYZE
45100 | NA - System | HYDRAULIC COMPONENTS | NA | 57 | 28 |  |  |  |  | See Watch List |  | NA | 4511P, 45175, and 45161 are all Fielded Components Breakdown ID'ed 4511P HP (fielded Sp1), 45175 Aux HP (fielded Sp1), 45161 Acc (fielded Sp2); 4511T lines (not recommended)
11140 | NA - System | AIRCRAFT WINDOWS | NA | 92 | 30 |  |  |  |  | See Watch List |  | NA | Breakdown ID'ed large quantity of scheduled mx events; aborts from 1114H P/CP, 1114J windshield, and 1114A boom sight
46240 | NA - Assembly | NO 4 MAIN | NA | 136 | 17 |  |  |  |  | See Watch List |  | NA | Assembly breakdown ID'ed pumps result in some aborts and mostly sched mx actions at ISO and PDM; not analyzing 46240
46130 | NA - Assembly | NO 1 MAIN | NA | 138 | 15 |  |  |  |  | See Watch List |  | NA | Assembly breakdown ID'ed pumps result in some aborts and mostly sched mx actions at ISO and PDM
11230 | 1560-00-331-4843 | CREW ENTRY DOOR | NA | 29 | 29 |  |  |  |  | 11230 Plan |  | NA | [8 empty] | x

## Watch List
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments
Data Transfer Unit | 7025-01-525-6110 | 729K0 | T&R | Contractor | Constraints Analysis / Watch List | Supply Constraints | Part Failure (High Break Rate) | CSAG funding |  |  |  | Supply constraint root cause: Contractor Performance (Collins Aerospace)Capacity/late to need during the early part of 2020 WIP quantities dropped to a critical level. WIP levels were restored in Aug 2020. New procurement of 56ea EDD NLT 31 July 2021; 50ea rec'd so far Supply = healthy Get well date: January 2022 Top driver due to supply constraints There was a soldering issue that cause pins to bend when the cards were inserted CSAG funding issues in 2020 also caused supply issues; supply health has recovered Action Item: PavCon to analyze last two years of data only. Short/medium term fix in work: Watchlist Risks (threats): NA Risk Mitigation Actions Gov Council discussion (for short term): NA Risk Mitigation Action for Gov Council discussion (long term): NA |  | WATCH LIST
Centering Cylinder | 1650-01-582-2429 | 13AHF | Overhaul | Hill AFB | Constraints Analysis / Watch List | Ineffective mod; correct mod needs implementing | [5 empty] | Supply constraint root cause: No current supply constraint analysis being performed. ACTION: Tracy...request 638 and 748 supply constraints...TBD Team moved to constraint analysis/watch list Part underwent modification which was not successful; aircraft reverted back to part prior to modification SPO provided to PavCon the date that each tail was reverted Action Item: PavCon to update histograms to view only data since reverting to original part. Short/medium term fix in work: Watchlist Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): NA Risk Mitigation Action for Gov Council discussion (long term): NA |  | WATCH LIST
No. 1 Main | N/A - System | 46130 | NA | NA | Constraints Analysis / Watch List | UNK | [5 empty] | Both fuel tanks have dropped significantly in rankings from the December 2020 to May 2021 top drivers lists; team agreed to continue watching to ensure they remain off the top drivers list Action Item: PavCon to rerun breakdown analyses using only 12-month data - COMPLETE |  | WATCH LIST
No. 4 Main | N/A - System | 46240 | NA | NA | Constraints Analysis / Watch List | UNK | [5 empty] | Both fuel tanks have dropped significantly in rankings from the December 2020 to May 2021 top drivers lists; team agreed to continue watching to ensure they remain off the top drivers list Action Item: PavCon to rerun breakdown analyses using only 12-month data - COMPLETE |  | WATCH LIST
MLG System | N/A - System | 13A00 | NA | NA | Constraints Analysis / Watch List | Part Failure (High Break Rate) | [5 empty] | Supply constraint root cause: Short/medium term fix in work: The team is interested in seeing the breakdown analyses for only the last 12 months Action Item: PavCon to rerun breakdown analyses using only 12-month data - COMPLETE Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): |  | WATCH LIST
Power Management Control | 2915-01-286-5565 | 27HAJ | T&R | Contractor | Constraints Analysis / Watch List | Part Failure (High Break Rate) | Supply Constraints |  |  |  |  | Supply constraint root cause: Short/medium term fix in work: According to Mr. Neal Camren, this part is often written up in the field for actual failures on other parts; the component is already serially tracked Removed and tested only at PDM Contractor is not meeting quarterly demands: zero MICAPs but 33 backorders Action Item: Mr. Dave Hollenbeck took an action to have WUC 27HAJ added to the serial number tracking report regularly provided to PavCon: COMPLETE - AMC provided 3 years SN data to PavCon; not sufficient data to make significant impact to analysis Action Item: PavCon to use serial number tracking report to determine if Never Seens can be reduced Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): |  | WATCH LIST
Computer Flight Control | 6615-01-138-2369 | 52210 | XD2 (confirm if OH or T&R) | Tinker AFB | Constraints Analysis / Watch List | UNK | [5 empty] | Supply constraint root cause: Short/medium term fix in work: It is suspected that the field units are removing and replacing the computer without walking through the troubleshooting tree No Engineering Technical Assistance Requests (ETARs) have been received lately on this part RCA was discussed for this part, but the team decided to put on watch list for now; a main operating base (MOB) visit and TO review may be warranted Action Item: Mr. Schwartz to work with SPO team to review the TO Action Item: Mr. Hollenbeck to communicate with field on troubleshooting versus premature part replacement Action Item: Mr. Hollenbeck to look more into why this part is a top driver Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): |  | WATCH LIST
Mode S/IFF Transponder | 5841-01-556-3173 | 65DAA | XD2 (confirm if OH or T&R) | Contractor | Constraints Analysis / Watch List | CANNs / Supply Constraints | [5 empty] | Supply constraint root cause: Short/medium term fix in work: An attendee provided the new NSN for this part as 5841-01-645-6210 (old NSN reported as 5841-01-556-3173) Part originally on list due to high number of cannibalizations (CANNs), but is now supply healthy with 200% RO Component is used on multiple platforms whose software was not compatible with the transponder; item manager froze all assets as a result; KC-135 units can update their own software and the parts were released in May 2021 Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): |  | WATCH LIST
Hydraulic Components | NA - System | 45100 | NA | NA | NA - Omit due to 45110 | UNK | FFP vs MOD |  |  |  |  | Supply constraint root cause: Short/medium term fix in work: No discussion warranted outside of discussion above on the hydraulic system, WUC 45110 Omit due to 45110 Action Item: PavCon to rerun breakdown analyses using only 12-month data - COMPLETE Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): |  | REMOVED FROM CONSIDERATION
Aircraft Windows | NA - System | 11140 | NA | NA | Constraints Analysis / Watch List | Part Failure (High Break Rate) | DLA |  |  |  |  | Supply constraint root cause: Short/medium term fix in work: Crazing issues on windows addressed AMC noted MTBF is now at 912 Action Item: PavCon to rerun breakdown analyses using only 12-month data - COMPLETE Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): |  | WATCH LIST
FDR/CVR Section | NA - Assembly | 51LA0 | NA | NA | Constraints Analysis / Watch List | Part Failure (High Break Rate) | IIRP |  |  |  |  | Supply constraint root cause: Short/medium term fix in work: Top drivers identified through breakdown analysis are WUC 51LAA on 1-n list and 51LAM which has FFF replacement for 2024+ No additional items warranted for assembly Action Item: PavCon to rerun breakdown analyses using only 12-month data - COMPLETE Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): |  | WATCH LIST
Ruddevator | 002499370 016506340 | 46766 | Overhaul | UNKNOWN | Constraints Analysis / Watch List | Supply Constraints | [5 empty] | Supply constraint root cause: Carcass constraints, backshop workflow constraints Short/medium term fix in work: New part design was procured but manufactured incorrectly and not installed; currently carcass constrained and backshop workflow issues exist (working backorders)Long term solution is already in place Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): |  | WATCH LIST
MMR System | N/A - System | 71300 | NA | NA | Constraints Analysis / Watch List | Part Failure (High Break Rate) | IIRP | FFP vs MOD |  |  |  | Supply constraint root cause: Short/medium term fix in work: GATM should not be included in the title of this part (REMOVED) No discussion warranted above what was already discussed for the MMR Action Item: PavCon to rerun breakdown analyses using only 12-month data - COMPLETE Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): |  | WATCH LIST
TCAS / VSI | 014332219 015272395 | 73AD0 | T&R | Contractor | NA - Omit due to removal from a/c | NA | [5 empty] | Part / WUC removed from aircraft per TCTO in 2019; indicator is now a part of the MFD - WUC removed from CBM+ consideration or analysis since no longer on the aircraft Action Item: SPO to remove WUC from -06 |  | REMOVED FROM AIRCRAFT

## IFMP 51FB0
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Integrated Fuel Management Panel (IFMP) | 6610-99-732-8120 | 51FB0 | T&R | Organic Test and minor repair at Hill AFB Major repair at BAE | Root Cause Analysis | Part Failure (high break rate) | Vendor Issues | Contract shortcomings | MODs | Root Cause Study |  | Supply constraint root cause: Capacity/Capability Issues: (BAE) Ogden Organic shop can only do minor repair. In-depth repair contract with BAE; del sch. of 4ea/120days. Vendor has cited test equipment and obsolescence as sustainability issues. Engineering effort has been canceled. NSN will be replaced in 2027 (unfunded). Short term fix in work: None: RSO/PavCon initiate RCA to identify potential short term solutions Risks (threats): BAE willingness to negotiate Risk Mitigation Actions Gov Council discussion (for short term): - Tracy, Jeremy, Brandon, Dell Plan A 1. Go to BAE...use other BAE business as leverage to push BAE to fix this issue (upgrade test stand, INCREASE production, refresh the part, etc). - Tracy to ask "loggy" if SC has contacted BAE 1a. Modify existing contract - feasible due to timing? 1b. Add MDR reqts, minimum life / PBL, CBM+ language into Aug/Sep 2022 contract 2. Minor repair performed at Ogden currently...purchase data rights (negotiate) or collaborate with BAE to build USAF test stand and then have Ogden (or other) can do more repair organically? I have in notes that if BAE refuses the contract, then they must provide the data rights to the USAF...so why would we purchase them? 3. Secure and protect the funding for Long term CCR mod. Long term Fix: Part of Center Console Refresh (CCR) modification NOT FUNDED (est 2027/2028). Risks (threats) for long term: Funding Loss
Notes on Part from Constraints Analysis Meeting
Test and check and minor repair completed at Ogden Air Logistics Complex (ALC); major repair conducted by BAE
BAE has an unreliable test stand
Currently, 50 IFMPs in F condition; BAE contract is for two MDR
Plan of Action
Short Term:
• Option 1: Modify current contract to update test stand and meet AF MDR
• Option 2: Add test stand update, CBM+ language, and PBL into 2022 contract
• Option 3: If BAE refuses to bid, BAE must provide data rights to the AF who will stand up organic capability
Long Term: Center console refresh (CCR) planned for 2027+ is unfunded
Action Items
Action Item: Ms. Tasha Miles track short term contract actions
Action Item: PavCon to determine through RCA efforts why part is failing in the field.
Notes from Parts Update Meeting 13 Jan 22
Meeting w/ Mocio and Hall; Tim Ness work with BAE to upgrade test stand - waiting on contract expiration in Aug 2022
Tim Ness, Depty Squad Comm 422nd
CCR still unfunded; AMC briefing to package as single initiative
Robin Adee, Section chief for contract, is working on contract side
Lisa Syth working on Tim Ness team
Strategic contracting may be viable option for BAE due to difficulty working with CTR
Contract to BAE to upgrade the test stand has been awarded; work not yet started - 15 months to just upgrade the test stand - will not increase throughput until test stand upgrade is complete
Option for CLS contracting w/ SPO
Explore 3D printing (or other technology) for the Faceplate versus ordering new IFMPs
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Track short term contract actions |  |  |  | Tasha Miles
Determine thru RCA why part is failing in field |  |  |  | PavCon | COMPLETE | Results included in All In Final Report
Comms w/ Robin and Lisa on next steps; potential to add increased throughput into contract (current 2 MDR) |  |  |  | Tracy Frazier | OBE | See below
Follow up with team w/ new contract MDR expectations |  |  |  | Emma Roza | COMPLETE | 15/month supply chain trying to negotiate with BAE - following test stand upgade
Explore potential to 3D print (or other tech like injection molding, etc.) the faceplates |  |  |  | Dewayne Jones | 2022-03-01 | RSO AM is one option
Talk to Paul Hoss about FDR upgrade capability and parameter reading on fuel boost pump switches (also push button valve switches) |  |  |  | Dewayne Jones | COMPLETE | Both capabilities added to new FDR refresh list

## CCM 729QC
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Common Computing Module (CCM) | 6610-01-501-3600 | 729QC | T&R | Rockwell Collins | Solution Implementation | Vendor Issues and Contract Shortcomings | IIRP | CSAG Funding | Part Failure (High Break Rate) | TCTO/Software load issues |  | Supply constraint root cause = Contractor performance Carcass short Short term fix in work: (Rockwell Collins) Shared test stand. Contractor working to increase output to 25-35ea/month to reduce backlog. Currently 40 failing in field monthly. Contract modification to add 501 P/N was completed on 6 Jan 21. Up the MDR. Contract expires August 2022. CBM+ language needs adding to contract. Risks (threats): CSAG funding loss, No data rights (vendor), lack of carcasses, costs associated with contract mods, ownership (gov versus vendor) of test stand will impact costs Risk Mitigation Actions Gov Council discussion (for short term): Plan A 1. Incentivize Collins to increase TOW (reliability clause / PBL contract) and Collins must meet changing demand requirements / minimum MDR - Tracy Leads Plan B 2. If Collins refuses contract requirements, AF establishes I-level capability (Collins reps at the base? Collins owns tech data.) Would require purchase of test stand at USAF installation. - Beth leads 2a. Setup repair site? - Supply Chain (TBD) 2b. Consider existing test stand locations to work these? New data set to be analyzed in support of Plans A and B - Mary B Long term Fix: Refresh 2024/2025 Choice #1 This item will be used as a pilot to add reliability language to the contract...utlize C130 as baseline. |  |  | SPO developing a new CCM | Type 1 | FFF | CSAG S | 8 | Forced Generation | Yes | Supply Chain and SPO to develop IIRP Package |  |  |  | SPO to let RSO know?? |  |  | SPO needs some help expediting IIRP (signatures for example)
Notes on Part from Constraints Analysis Meeting
Form fit function (FFF) replacement / refresh in works with 2025 install date
Rockwell Collins not producing enough parts to meet Air Force (AF) demand; current contract is for 20 monthly demand rate (MDR) yet actual MDR is closer to 40 parts
Current contract expires August 2022 - have time to make modifications
There was a Technical Order (TO) change that went into effect in February 2021; field change
PavCon previously analyzed CCM as part of Spiral 2
Plan of Action
Short Term: Add CBM+ language into the sustainment contract (current contract ends August 2022); adjust contract to meet MDR; establish performance-based logistics (PBL) construct
• Option 1: Collins meets new contract requirements; AF incentivizes Collins to increase time on wing (TOW) reliability
• Option 2: Collins rejects contract and AF established I-level capability
Long Term: 2025 refresh; consider field-level repair of refresh part
Action Items
Action Item: Ms. Tracy Frazier lead on Options 1 and 2 from Air Force Sustainment Center (AFSC) and Ms. Elizabeth Hottle will lead from SPO
Action Item: PavCon will update histograms to view last six months and 12 months to determine if TO changes have had any affect
Notes from Parts Update Meeting 13 Jan 22
Second phase of CCM refresh contract
IIRP paperwork in process to procure more CCMs (forced replacement at PDM or TCTO in field)
Col Hall (AFSC) in comms with Collins - not talking about increased reliability though
Strategic Contracting may be viable option for increasing MDR and SOH for CCM/IOC
Col Mocio willing to participate in mtgs with Col Hall and Collins Execs
Col Tate, SSRM - working with Col Hall on Collins contracting
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Lead efforts to mod Collins contract to increase TOW and/or establish I-level capability |  |  |  | Tracy Frazier |  | 11/2/2021 - setting up small working group to begin discussions within SC 11/16/2021 AFSC mtg scheduled with AFSC/PZA to discuss repair contract process flow
Lead efforts to mod Collins contract to increase TOW and/or establish I-level capability |  |  |  | Beth Hottle
Update histograms w/ last 6 and 12 month data only |  |  |  | Shawn Driscoll, Mary Bush | COMPLETE | Histograms, Weibulls, and profile pages are complete
Talk w/ Mocio about attending mtgs w/ Col Hall and Collins for increased reliability and MDR; overall CBM+ discussions as well |  |  |  | Dewayne Jones | 2022-01-31 | In conjunction with Collins PMR in Jan/Feb; invite RSO from CBM+ enterprise perspective
Talk w/ Hall about attending mtgs w/ Col Mocio and Collins for increased reliability and MDR; overall CBM+ discussions as well |  |  |  | Tracy Frazier | 2022-01-31 | Meeting being scheduled by Col Tate

## MFD 51JA0
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Multifunction Display MFD-255K | 5841-01-504-5586 | 51JA0 | T&R | Rockwell Collins | Root Cause Analysis | Part Failure (High Break Rate) | Vendor Issues | CSAG Funding |  |  |  | Supply constraint root cause: Contractor Performance Short term fix in work: (CollinsAero.) Constrained by no SOS for LCD Glass; new glass was approved. PR qty194 for adding LCD Glass and Graphics Cards. Lack of funding for DOR delayed repair. Awarded 23 Jul 21. SOH at Contractor. 45 days After Receipt Order. - Get well date January 2022...supply chain - RSO/PavCon initiate RCA to identify potential short term solutions - This part is a Top priority for 448th study due to impact on fleet Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): none Long term Fix: Refresh 2027/2028 NOT FUNDED Risk Mitigation Action for Gov Council discussion (long term): 1. Secure and protect funding for Modification (CCR modification)
Notes on Part from Constraints Analysis Meeting
Obsolescence issues so part is only repaired; cannot obtain glass
New requirement with contract for 45 MDR, 50 MDR maximum, 45-day turnaround; implemented 23 Jul 21
Product Quality Deficiency Report (PQDR) quantities are high on MFD; issues encountered with field submitting PQDRs but not sending in the part
• Policy change may be needed to ensure parts are submitted from field to source of supply to contractor, if needed, within a reasonable timeframe
• Mr. Jeremy Schwartz agreed to look up PQDR details in the Joint Deficiency Reporting System (JDRS)
• Mr. Del Hodge noted that the action point is typically the Equipment Specialist and 120 days is typical for completion
• SMSgt Seth Holliger added that the parts are held at the unit awaiting disposition and questioned who tells the field where to send the part; the
Plan of Action
RCA should include research into how many PQDRs are written and how many were rejected or sent back
Short Term: Ms. Miles to track short term contract actions, including CBM+ and PBL language into contracts
Long Term: CCR planned for 2027+; unfunded
Action Items
Action Item: Mr. Schwartz to look up PQDR details in JDRS
Action Item: Ms. Miles to track short term contract actions
Action Item: PavCon to determine through RCA efforts why part is failing in the field.
Notes from Parts Update Meeting 13 Jan 22
AFOSI - fradulent repairs by Collins? Investigation underway.
Tony Simmons, Robins loggies, lead, 407th; Dewayne sharing info with Tracy and Tasha
Long term solution - part of CCR (larger screen), CCR unfunded
Nov 2020 corporate contract
QDR 110, produced 500+
Lifetime procurement on glass 2-3 years ago; Collins filled backorders (almost caught up), but once small glass is used, no more until larger screen mod
Looks positive but team anticipate part health declining in near future
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Look up PQDR details in JDRS on MFD |  |  |  | Jeremy Schwartz | 2022-01-31
Track short term contract actions |  |  |  | Tasha Miles | COMPLETE | Delivery order requests expected as usual biz ops
Determine thru RCA why part is failing in field |  |  |  | PavCon | COMPLETE | Results included in All In Final Report
Look into mod: CCR? |  |  |  | Dewayne Jones | 2022-01-31
Inquire with Tony Simmons estimates on when lifetime procurement on small glass is expected to be used / gone |  |  |  | Tasha Miles | 2022-01-21

## IOC 729QB
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Input Output Concentrator (IOC) | 6610-01-502-0350 | 729QB | T&R | Rockwell Collins | Solution Implementation | Vendor Issues and Contract Shortcomings | TCTO/Software load issues | Part Failure (High Break Rate) | CSAG Funding | IIRP |  | SAME AS CCM Supply constraint root cause = Contractor performance Carcass short Short term fix in work: (Rockwell Collins) Shared test stand. Contractor working to increase output to 25-35ea/month to reduce backlog. Currently 40 failing in field monthly. Contract modification to add 501 P/N was completed on 6 Jan 21. Up the MDR. Contract expires August 2022. CBM+ language needs adding to contract. Risks (threats): CSAG funding loss, No data rights (vendor), lack of carcasses, costs associated with contract mods, ownership (gov versus vendor) of test stand will impact costs Risk Mitigation Actions Gov Council discussion (for short term): Plan A 1. Incentivize Collins to increase TOW (reliability clause / PBL contract) and Collins must meet changing demand requirements / minimum MDR - Tracy Leads Plan B 2. If Collins refuses contract requirements, AF establishes I-level capability (Collins reps at the base? Collins owns tech data.) Would require purchase of test stand at USAF installation. - Beth leads 2a. Setup repair site? - Supply Chain (TBD) 2b. Consider existing test stand locations to work these? New data set to be analyzed in support of Plans A and B - Mary B Long term Fix: Refresh 2024/2025 Choice #1 This item will be used as a pilot to add reliability language to the contract...utlize C130 as baseline.
The CCM/IOC are following the same All-In approach since they are a part of the same assembly and the solution will be the same
FROM CCM PAGE
Notes on Part from Constraints Analysis Meeting
Form fit function (FFF) replacement / refresh in works with 2025 install date
Rockwell Collins not producing enough parts to meet Air Force (AF) demand; current contract is for 20 monthly demand rate (MDR) yet actual MDR is closer to 40 parts
Current contract expires August 2022 - have time to make modifications
There was a Technical Order (TO) change that went into effect in February 2021; field change
PavCon previously analyzed CCM as part of Spiral 2
Plan of Action
Short Term: Add CBM+ language into the sustainment contract (current contract ends August 2022); adjust contract to meet MDR; establish performance-based logistics (PBL) construct
• Option 1: Collins meets new contract requirements; AF incentivizes Collins to increase time on wing (TOW) reliability
• Option 2: Collins rejects contract and AF established I-level capability
Long Term: 2025 refresh; consider field-level repair of refresh part
Action Items
Action Item: Ms. Tracy Frazier lead on Options 1 and 2 from Air Force Sustainment Center (AFSC) and Ms. Elizabeth Hottle will lead from SPO
CCM Action Item: PavCon will update histograms to view last six months and 12 months to determine if TO changes have had any affect - PavCon did not take action on IOC. Needed??
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Lead efforts to mod Collins contract to increase TOW and/or establish I-level capability |  |  |  | Tracy Frazier |  | 11/2/2021 - setting up small working group to begin discussions within SC 11/16/2021 AFSC mtg scheduled with AFSC/PZA to discuss repair contract process flow
Lead efforts to mod Collins contract to increase TOW and/or establish I-level capability |  |  |  | Beth Hottle

## E-TCAS 73AA0
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
E-TCAS Processor (TPS-81A) | 5841-01-470-8036 | 73AA0 | T&R | Contractor | Root Cause Analysis | Part Failure (High Break Rate) | [5 empty] | Supply constraint root cause: b. Undergoing add’l modification c. No current supply constraint analysis being performed Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Undergoing additional modification. Consider purchase new version NSN: 5841-01-641-1494 versus old version. ACTION: Jeremy/SPO RCA - determine cost benefit of new versus repair. Determine if other airframes are experiencing issues? Long term: ACTION SPO: Discuss with Honeywell...need long term repair/sustainment plan. Risks (threats): NA Risk Mitigation Actions Gov Council discussion (for short term): NA Risk Mitigation Action for Gov Council discussion (long term): NA
Notes on Part from Constraints Analysis Meeting
New $66,000 MIL Airborne Collision Avoidance System (ACAS) is available and software compatible, but initial cost benefit analysis was not successful; the team made additional recommendations of items to include in a cost analysis to be more inclusive
Part used on KC-135 and C-130J models; all Mission Incapable (MICAP) Supply stats are on the KC-135
16 Aug - 200 carcasses for repair; Honeywell continuing to repair
Action Items
Action Item: PavCon to determine through RCA efforts why part is failing in the field
Action Item: AMC took an action to provide cost of lost time calculation on part to assist with cost justification.
Action Item: Foreseeable constraints with obsolescence or Honeywell refusing to repair (initially in 2016 stop work) - get long term plan from IM/ES (Action Tracy Frazier)
New Info 17 Sep 21 from Tracy:
FY21 DOR FA853921F0023 awarded on 28 June 2021 for the qty of 59EA to meet MICAPS and SURGEs requirements. All units were shipped on 1 July 2021, TAT 30 days after receipt of carcass.
Remaining quantity to be produced: 57.
FY21 DOR: FA853921F0050 awarded on 16 Aug 2021 for the QTY: 240ea.Carcasses will be shipped once the contractor can accommodate additional carcasses at their repair's facility.
Notes from Parts Update Meeting 13 Jan 22
Depot has 120, Honeywell has 200+ carcasses for repair
Bases have A cond
WG at Robins working on long term plan; Honeywell will eventually stop repair on current design
White paper from Collins - FFF
Block v Block 45 - approx 50% upgraded; FY25-26 upgrade completion on 45 to fleet
Option: Breakout analysis on Block 40 v Block 45 to view clean failures. Is new 45 more reliable?
Same design - improved feed btw block (no new actual component)
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Determine thru RCA why part is failing in field |  |  |  | PavCon | COMPLETE | Results included in All In Final Report
Provide Cost of Lost Time calculation on E-TCAS to assist with cost justification for MIL ACAS |  |  |  | Dave Hollenbeck | COMPLETE | Cost of Lost Time values provided by AMC for MICAPs only for FY20 and FY21; PavCon requested the remaining calculations, if possible to provide
Get long term plan from IM or ES to address constraints with obsolescence or Honeywell refusing to repair |  |  |  | Tracy Frazier | COMPLETE | 11/15/2021 - Sent follow on email to IM
Support cost justification of new MIL ACAS $66K |  |  |  | SMSgt Webb | 2022-02-28 | Work with Dewayne Jones, SPO
Consider / fund breakout analysis on Block 40 v Block 45 data to view clean failures and determine if 45 is more reliable |  |  |  | Jason Trout | 2022-02-28 | PavCon generated on another LRU

## MMR 713A0
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Multi-Mode Receiver (MMR) | 5895-01-500-7538 | 713A0 | T&R | Collins (needs confirmation) | Root Cause Analysis | Supply Constraints | Obsolescence | TCTO/Software load issues | Part Failure (High Break Rate) | IIRP |  | Supply constraint root cause: Contractor Performance (Collins Aerospace) Contractor has one test stand and limited personnel that runs tester; discussions with contractor resulted in push for production of 16/month Part Health: 66BOs no MICAPs Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Discussions with contractor resulted in push for production of 16/month TO change published, TCTO released. Obsolescence issues with current. Action Jeremy - Need newer data to perform RCA and verify TO change Long term - Collins identified a new part to replace this one. Is this FFF vs Mod. Potential IIRP "bucket". Action DeWayne - work with SPO engineering to determine how quickly the new mod with updated GPS will be implemented. NOTE: potential candidate for overhaul process organic or vendor versus current test and repair process ACTION Dewayne - see if mod package is in work to address this. Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Not at this time Risk Mitigation Action for Gov Council discussion (long term): Not at this time
Notes on Part from Constraints Analysis Meeting
SPO previously attempted a Time Compliance Technical Order (TCTO) for a software load procedure, but the action was not supported
No fault findings (NFFs) are high but have reduced from ~50% to ~20% after TO modifications; team interested in seeing histograms with only one year of data to determine TO modification success
Obsolescence data provided quarterly by Collins; Collins identified potential alternatives that were non-FFF
There is no modification programmed or in place
Action Items
Action Item: PavCon to generate histograms with most recent one year of data
Action Item: Mr. Dewayne Jones took an action to determine the extent of the obsolescence issues
Notes from Parts Update Meeting 13 Jan 22
Corroded connectors; MMRs arriving from supply without heat wrap on wiring
Add heat wrap to wiring; organic built wiring includes heat wrap and results in increased performance - Who makes or provides the wiring??
End of repair supportability analysis - 2027
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Generate histograms (update eRCM analysis) with most recent one year data |  |  |  | Shawn Driscoll, Mary Bush | COMPLETE | Histograms, Weibulls complete; profile pages complete
Determine extent of the obsolescence issues on MMR |  |  |  | Dewayne Jones | 2022-01-31 | Collins stop repairing MMR in 2027; Dewayne initiating a 1067 (joint SPO/AMC process and document)
Refresh technology or modification program? New tech contains GPS which is new capability = not FFF (cannot use CSAG funds) |  |  |  | Dewayne Jones | 2022-01-31 | Iniitiate 1067 if truly new requirement / new tech

## FMAC 51FA0
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Fuel Management Advisory Computer (FMAC) | 014352935 | 51FA0 | T&R | Organic Test and minor repair Major repair at Contractor | Root Cause Analysis | Part Failure (High Break Rate) | Refresh - Long Term | MODs |  |  |  | Supply constraint root cause: Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term): |  | NOT FUNDED
Notes on Part from Constraints Analysis Meeting
The FMAC is a test and check item with organic minor repair and BAE contractor major repair
New FMAC design was proposed with the IFMP/CCR with 2027+ potential install date, if funded; new design will eliminate the FMAC
It is unknown if BAE uses the same or different test stand as the IFMP (currently unreliable stand)
Action Items
Action Item: Mr. Schwartz to determine if the FMAC and IFMP use the same test stand
Action Item: PavCon to determine through RCA efforts why part is failing in the field.
Notes from Parts Update Meeting 13 Jan 22
Potential recommendation for TO modification (wiring v fuel probes in troubleshooting tree)
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Determine if the FMAC and IFMP use the same test stand |  |  |  | Jeremy Schwartz | COMPLETE | Same test stand; slightly diff fixtures but both are being upgraded with BAE contract (same as IFMP contract - 15 month upgrade)
Determine thru RCA why part is failing in field |  |  |  | PavCon | COMPLETE | Results included in All In Final Report

## FDR-CVR 51LAA
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Flight Data Recorder / Cockpit Voice Recorder (FDR/CVR) | 6610-01-462-5980 | 51LAA | T&R | Contractor | Root Cause Analysis | Vendor Issues and Contract Shortcomings | Obsolescence | IIRP |  |  |  | Supply constraint root cause: Contractor Performance GE Aviation Several Over & Above requests on previous repair contract impacted production due to long lead time. Follow-on repair contract awarded Sep 20; includes major and minor repair to eliminate this in the future. Delivery Schedule: Major Repair 5ea/90days and Minor Repairs 15ea/45days Get well Date: December 2021 Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Isn't IIRP a long term solution? If yes, move all below to long term fix. Assume IIRP takes years. Also, I thought the new FDR was already approved and in procurement with 2024 install date?? IIRP Package is with 422th that is reviewing. ACTION: Dave H to talk to POC at AMC A5/8 who declined package...Tracy will get the POC name to Dave H/Lt Col Scozzaro Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Hold until we hear from AMC Risk Mitigation Action for Gov Council discussion (long term): Hold until we hear from AMC
Notes on Part from Constraints Analysis Meeting
FDR has a long-term obsolescence issue
Needs improving within supply chain
It is unknown if a CSAG funding lapse affected the supply or availability of the FDR
Long Term: New FDR expected in 2024 through IIRP; team needs to ensure that CBM+ language is written into the contract for the new item
Replacement is planned via field units via TCTO
Retest OK (RTOK) rate of 5% per Ms. Frazier
Action Items
Action Item: Ms. Frazier to determine if CSAG funding was an issue in recent years
Action Item: PavCon to breakout analysis based on temperature and location.
Notes from Parts Update Meeting 13 Jan 22
New FDR still planned for FY24; CSAG funding for refresh
Forced replacement at PDM or field TCTO
Current FDRs still being repaired; repair contract thru Sept 2025
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Determine if CSAG funding was an issue in recent years |  |  |  | Tracy Frazier | COMPLETE | No funding issue, Asset is no longer procurable, IIRP effort in works, FORM 564 at AFMC
Run eRCM analysis based on temperature and location |  |  |  | Shawn Driscoll | COMPLETE | Date broken out into regions based on temp and location; profile pages in development
Provide update on IIRP status and projected approval dates; confirmation on FY24 procurement |  |  |  | Tracy Frazier | 2022-01-31 | 30 Mar 2022 sent email to 422d to try and track down IIRP package, PID shows formal package and AFMC form 564 is "currently in work"

## 72800 & 728C0
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
WXR-700X Color Weather Radar System | N/A - System | 72800 | NA | NA | Root Cause Analysis | Part Failure (High Break Rate) | IIRP | CSAG Funding |  |  |  | Supply constraint root cause: Contractor Performance Short/medium term fix in work: (CollinsAero.) Rockwell production rate does not satisfy MDR of 32; new TAT is 45 days ARO / Max of 20 per month-Min of 15 per month. MICAP get well date 21 December Overall get well date 23 December RSO/PavCon initiate RCA to identify potential short term solutions Isn't IIRP a long term solution? If yes, move all below to long term fix. Assume IIRP takes years. SPO would like to initiate an IIRP package to replace this part during PDM. Collins has recommended a newer version as this item is obsolete...SPO recommend supply purchasing this new part and SPO/engineering designing a new installation package. Action - Dewayne Jones to gather data on reliabilty of the new part with Collins and USAF engineering. Action - Jeremy S/DeWayne J. to compose IIRP package for this item Action - AMC to review AFTER IIRP package is complete Action - Brandon/Dell to work with SPO and HAF to use this IIRP as the example regarding why we need update 23-101. Ask Dan Christianson to get a copy of new IIRP language and work with him. Keeping Mr. Lamb in the loop. Risks (threats): Corporate contract with Collins already awarded. Without quarterly computation telling supply chain to purchase these items...SC cannot make that purchase. Risk Mitigation Actions Gov Council discussion (for short term): 1. Ask council to support IIRP. Ask panel to help AMC get funding. Exact details TBD based on collaboration between SPO, AMC and RSO. Long term Fix: Not required (assuming new part TOW meets requirements) Risk Mitigation Action for Gov Council discussion (long term):
Weather Receiver Transmitter WRT-701X | 5841-01-432-3798 | 728C0 | T&R | Collins Aero | Root Cause Analysis
Notes on Part from Constraints Analysis Meeting
Field improvement is needed on data entry; ideal to use five-digit not three-digit WUC for proper documentation
Mr. Anthony Simmons noted that he has investigated but has not identified a drop-in replacement for this system; Mr. Russ Alford noted that the C-5 is working on a full system replacement
According to Collins, 2030 is the end-of-life date for this system; there is no long-term plan due to the reliability issues
It was noted that a 1067 with justification will not suffice in this situation
Team discussed whether this system is more appropriate for FFF (sustainment / AFSC funds) or the Improved Item Replacement Program (IIRP)
Action Items
Action Item: Mr. Simmons is lead on determining if Collins has a recommendation for a drop-in replacement
Action Item: Mr. Schwartz took an action to work with Ms. Anne Copeland, KC-135 Chief Engineer, to determine FFF versus modification.
Action Item: PavCon to rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38
Notes from Parts Update Meeting 13 Jan 22
Technology is not specific to Collins; interested in competitive solicitation versus Collins WRT
No program initiated for replacement
Collins corporate contract is viable until Oct 2030
Producing 20+ per month currently (increased throughput)
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Determine if Collins has a recommendation for a drop-in replacement for the color weather radar system |  |  |  | Anthony Simmons | COMPLETE | Yes, Collins has a solution but SPO leadership does not want to sole source; competition solicitation
Work with Ms. Anne Copeland, KC-135 Chief Engineer, to determine FFF versus modification |  |  |  | Jeremy Schwartz | 2022-01-31 | Dewayne will discuss with Jeremy; joint conversation with Tracee Sealy, Dir Engineering 638th, Robins
Rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38 |  |  |  | Shawn Driscoll, Mary Bush | COMPLETE | Breakdown analyses completed with 18-month data; profile pages generated

## Starter 27CBA
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Starter | 2995-01-140-2105 | 27CBA | Overhaul | Hill AFB | Root Cause Analysis | DLA Supply Constraints | Part Failure (High Break Rate) |  |  |  |  | Supply constraint root cause: Parts (Organic)Repair has been impacted my multiple piece part constraints.. Shop is AWP for a DLA managed retaining ring (5325-01-162-2853SX) 1 @ 100% , Contract in place with Parker Hanifin for 110 ea with a Aug 21 EDD. Shop has approved the reuse of DLA ring when feasible until new buy units from deliver. Check COPA for DHA’s on DLA ring Supply Healthy - yes Short/medium term fix in work: ACTION: RSO/PavCon initiate RCA to identify potential short term solutions Jeremy - compare field failures versus depot failures. I had this as a PavCon Neal action to determine if main driver is PDM/engine removals of F in field; recorded no actions for Jeremy Track by starts versus flight hours...for CBM+ implementation. Check FDR (aircraft sortes as a second option) to determine when recording starts/ends Risks (threats): no Risk Mitigation Actions Gov Council discussion (for short term): no Risk Mitigation Action for Gov Council discussion (long term): no
Notes on Part from Constraints Analysis Meeting
According to Mr. Gerald Harris, this part has issues with Defense Logistics Agency (DLA) piece parts and a demand data exchange (DDE) has been submitted on certain replacement parts (e.g., retaining ring)
30% RO
Team questioned whether the main driver is failures in the field or engine removals at PDM; it was noted that the starter is removed and tested during engine overhauls at PDM but may not be put back on the same engine causing a lost position at PDM situation
Action Items
Action Item: Ms. Frazier and Mr. Harris will track the supply posture to ensure part gets/stays healthy
Action Item: PavCon to investigate the lost positions in the maintenance (Mx) data and then rerun analysis
Action Item: PavCon to investigate potential to utilize FDR data for eRCM
Action Item: PavCon to conduct RCA to include tracking of starters through the remove and reinstall process at PDM.
Notes from Parts Update Meeting 13 Jan 22
88 backorders; shop producing over QDR - positive trend
Still some issues with DLA managed parts
Guard engines not serviced at PDM - in field only
Contractor repairing some engines as well (Struther Field) - may only be off load capacity
F-108 engine mod, CFM Propulsion Upgrade Program (CPUP) - unsure of starter tracking during CPUP
Option: Starter control valve and starter control box - potential to conduct eRCM analysis
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Track the supply posture to ensure parts gets / stays healthy |  |  |  | Tracy Frazier / Mr. Harris | In Process | Shop is AWP for a DLA managed retaining ring (5325-01-162-2853SX) 3 @ 100% , Contract in place with Integrated Procurement Technologies for 500 ea with a 21 Jan 22 EDD, contractor will attempt to expedite and now project mid November shipment (assets are currently being packed) ERB has been closed and there's no surplus available
Investigate the lost positions in the mx data then rerun analysis |  |  |  | Neal Camren / Shawn Driscoll | COMPLETE | Analysis complete; profile pages developed
Investigate the potential to utilize FDR data for eRCM |  |  |  | Shawn Driscoll | OBE | Will require RSO action post sustainment efforts
Conduct RCA to include tracking of starters through the remove and reinstall process at PDM |  |  |  | PavCon | OBE | PDM discussions were not a part of initial RCA; will require RSO action post sustainment efforts
Consider / fund eRCM analysis on starter control valve and control box |  |  |  | Jason Trout | 2022-02-28

## 72HA0 & 72H00
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Embedded GPS Internal Navigation System (INS) (EGI) System | N/A - System | 72H00 | NA | NA | Root Cause Analysis | Part Failure (High Break Rate) | [5 empty] | Supply constraint root cause: Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term):
Embedded GPS Internal Navigation System (EGI) | 6605-01-426-8522 | 72HA0 | T&R | Contractor | Root Cause Analysis
Notes on Part from Constraints Analysis Meeting
It was noted that Robins is developing a new EGI; potential long-term solution
Consolidated Sustainment Activity Group (CSAG) funding shortfall in past likely reason part is a top driver; funding issues are resolved; supply is healthy
Team expressed an interest in determining if there are any other top drivers in this system outside of EGI, WUC 72HA0
Action Items
Action Item: PavCon to review narratives within WUC 72H00 in search of other potential top drivers; if significant entries for 72HA0 are identified, move them into this analysis
Action Item: PavCon to verify position on 72HA0 to note on one position (histograms may include 72HM0); rerun data with most recent one year and any new data from 72H00 narratives.
Action Item: PavCon to rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38
Notes from Parts Update Meeting 13 Jan 22
Can 12 channel be used in 5 channel position? 12 channel has increased performance over 5 channel (only 5 channel on 1-n drivers)
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Review narratives within 72H00 in search of other potential top drivers |  |  |  | Neal Camren | COMPLETE | No other top drivers identified outside of 72HA0 and 72HM0 (EGI 5 and 12 channel)
After review narratives within 72H00, if significant entries are for 72HA0, move them into the analysis |  |  |  | Neal Camren, Shawn Driscoll | NA | OBE
Verify position on 72HA0 to note only 1 position |  |  |  | Shawn Driscoll | COMPLETE | Revised analysis only includes 1 position
Rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38 |  |  |  | Shawn Driscoll, Mary Bush | COMPLETE | Breakdown analyses completed with 18-month data; profile pages generated
Speak w/ Paul Hoss: Long term solution of EGI and if there were sufficient quantities, could the 12 channel (LH, P) be used in the 5 channel position (RH, CP) |  |  |  | Dewayne Jones | 2022-01-31

## Res Brake 13CBM
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Reserve Brake Accumulator | 1650-00-877-6095 | 13CBM | XF3 | Field | Root Cause Analysis | DLA Supply Constraints | Contract Shortcomings |  |  |  |  | Supply constraint root cause: Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term):
Notes on Part from Constraints Analysis Meeting
Part is an XF3 managed by DLA
Part is not supply supportable; currently two on shelf with 56 backorders and October 2022 get well date
Team questioned how to get this part faster and noted the need to add a minimum life into DLA contracts
An attendee noted that DLA has processes that are not always conducive to a predictive Mx environment and questioned how DLA can change processes to ensure this does not occur in the future; engagement with DLA leadership is needed
Action Items
Action Item: Ms. Frazier to work with Mr. Rob Williams, DLA, on getting minimum life requirements into DLA contracts
Action Item: Mr. Lafferty to request RSO leadership engage with DLA leadership regarding the need for quick response processes.
Notes from Parts Update Meeting 13 Jan 22
Supply constraints remain; 0 SOH, 3 MDR, 17 on order w/ no projected delivery date
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Work with Rob Williams, DLA, on getting minimum life requirements into DLA contracts |  |  |  | Tracy Frazier | In progress | Per Rob Williams, Parker-Hannifin produces new parts for DLA. All DLA provides are Condition Code A-new equipment/factory new parts, Regarding the statement on minimum life requirements…is there currently data available suggesting the item is failing pre-maturely? I’m not sure I understand what’s being asked regarding modification. Are they saying modify the contract with some type of minimum life promise?
Request RSO leadership engage DLA leadership regarding the need for quick response processes |  |  |  | Lt Col Lasher | 2022-01-21 | RSO will provide update
Email histogram to Rob Williams as justification for increased life on contractor provided parts |  |  |  | Mary Bush | COMPLETE | eRCM results emailed to Rob Williams on 20 Jan 22

## CPC 41126
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Cabin Pressure Controller | 1660-01-290-2065 | 41126 | Overhaul | Tinker AFB | CBM+ Implementation | Part Failure (High Break Rate) | [5 empty] | Supply constraint root cause: Short/medium term fix in work: Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term):
Part fielded in June 2021 in eRCM and actively being removed; therefore, no further action warranted

## 41120
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Pressurization | N/A - System | 41120 | NA | NA | Root Cause Analysis | Part Failure (High Break Rate) | Data Integrity |  |  |  |  | Supply constraint root cause: a. Fielded 1660-01-290-2065 Cabin Pressure Controller (WUC 41126) Threshold set at 9000 hrs b. #24 on current 1-N list c. Fielded 4820-00-817-1939 Outflow Safety Valve (WUC 41123) Threshold set at 6000 hrs d. Not on 1-N list as of May 2021 data pull Short/medium term fix in work: RSO/PavCon initiate RCA specifically on OSV and CPC to identify potential short term solutions Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): NA Risk Mitigation Action for Gov Council discussion (long term): NA
Notes on Part from Constraints Analysis Meeting
Outflow safety valve and cabin pressure controller (both within this system) are fielded in enhanced Reliability Centered Maintenance (eRCM)
It was noted that the outflow safety valve may be nearing the end of its repair cycle; is there a way to correlate the number of repairs to life of a part?
Action Items
Action Item: PavCon to confirm that the outflow safety valve and cabin pressure controller are top drivers.
Action Item: PavCon to rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38
Notes from Parts Update Meeting 13 Jan 22
Option: Potential follow on RCA efforts on OSV and CPC as LRUs within pressurization system
Option: Watch list for system level 3 and 4 digit WUCs / not LRUs
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Confirm that the outflow safety valve and cabin pressure controller are top drivers |  |  |  | Shawn Driscoll, Mary Bush | COMPLETE | Confirmed within updated breakdown analyses, especially in qty Mx actions
Rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38 |  |  |  | Shawn Driscoll, Mary Bush | COMPLETE | Breakdown analyses completed with 18-month data; profile pages generated
Determine thru RCA why OSV and CPC are failing in field |  |  |  | PavCon | OBE | Not investigated since system; RCA focused on LRUs in Top 38
Consider / fund potential follow on RCA efforts on the OSV and CPC as LRUs within system |  |  |  | Jason Trout | 2022-02-28

## FMS 72900
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
FMS-800 Flight Management System | N/A - System | 72900 | NA | NA | Constraints Analysis | Supply Constraints / CANNs | [5 empty] | Supply constraint root cause: Contractor Performance (CollinsAero.) Rockwell production rate does not satisfy MDR of 32; new TAT is 45 days ARO / Max of 20 per mnth-Min of 15 per month Supply Health: Assuming vendor meets max/min monthly deliveries...short term we are healthy Short/medium term fix in work: Complete eRCM analysis on the 729B0 Control Display Unit (CDU) identified as a top driver. Improving CCM and IOC will positively impact this assembly. Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): NA Risk Mitigation Action for Gov Council discussion (long term): NA
Notes on Part from Constraints Analysis Meeting
In addition to the CCM, IOC, and IPC, the top driver in this system is WUC 729B0, Control Display Unit (CDU), NSN 6610-01-444-0953
CDU has known obsolescence issues; contractor repaired (Rockwell Collins) with 111 serviceable assets, 9% NFFs, and 55% requisition objective (RO)
Remain in Constraints Analysis until CDU analysis is complete
Action Items
Action Item: PavCon run eRCM analyses on the CDU
Action Item: 448th run supply analyses on the CDU
Notes from Parts Update Meeting 13 Jan 22
51% RO as of Jan 2022
Note from Tracy: High Voltage Power Supply (HVPS), P/N 270-0736-020, replacement rate 10%, risk identified as moderate based on current inventory. USAF does not possess data.
Collins will stop repairing the CDU in 2025; anticipate limited support in 2023
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Run eRCM analysis on the CDU |  |  |  | Shawn Driscoll | COMPLETE | Histograms, Weibulls complete; profile pages complete
Run supply analysis on the CDU |  |  |  | Tracy Frazier | COMPLETE | Provide similar quad to other parts?? (Yes please - Mary)
Determine reason for non-supportability of CDU |  |  |  | Tasha Miles | 2022-01-21

## 729Q0
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Integrated Processing Center (IPC) | N/A - Assembly | 729Q0 | NA | NA | Solution Implementation | Vendor Issues and Contract Shortcomings | CSAG Funding
No action as the CCM/IOC make up the IPC

## Hyd Sys 45110
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Hydraulic System | N/A - Assembly | 45110 | NA | NA | Root Cause Analysis | Part Failure (High Break Rate) | [5 empty] | Supply constraint root cause: Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term):
Notes on Part from Constraints Analysis Meeting
Mr. Wesley Durant joined the meeting to answer questions on the hydraulic system
As noted previously, the system breakdown analysis will be rerun to include only the last 12 months
WUC 4511T (shown on breakdown) is discontinued; deleted from -06 on 3 May 19; AMC confirmed during the meeting that 4511T no longer shows in G081
The engine hydraulic pump, WUC 4511P, is a potential IIRP candidate; fielded in eRCM currently
Action Items
Action Item: PavCon to rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38
Notes from Parts Update Meeting 13 Jan 22
4511P no longer an IIRP candidate due to mounting; will have to be a future modification if considered
CSAG funding shortfall caused backshop issues (tracking already in CBM+)
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38 |  |  |  | Shawn Driscoll, Mary Bush | COMPLETE | Breakdown analyses completed with 18-month data; profile pages generated

## Cabin AC Sys 41210
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Cabin Air Conditioning System | NA - System | 41210 | NA | NA | Root Cause Analysis | Part Failure (High Break Rate) | [5 empty] | Supply constraint root cause: Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term):
Notes on Part from Constraints Analysis Meeting
The water separator, WUC 41214, was identified in the breakdown analysis; Mr. Todd Downs noted that there is a recurring issue with the water sock in the separator freezing which affects the ability to pressurize the aircraft
Improvements recommended include making part a time change item or integrating high and low humidity separators into aircraft based on location
Action Items
Action Item: PavCon to determine through RCA efforts why part is failing in the field.
Action Item: PavCon to rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38
Notes from Parts Update Meeting 13 Jan 22
Water sock changed at ISO at some bases but not all; TO suggests change as needed
900 hour and PE - change at both potentially to get annual change
Recommendations on water sock
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Determine thru RCA why part is failing in field |  |  |  | PavCon | OBE | Not investigated since system; RCA focused on LRUs in Top 38
Rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38 |  |  |  | Shawn Driscoll, Mary Bush | COMPLETE | Breakdown analyses completed with 18-month data; profile pages generated
Consider / fund eRCM analysis on water sock |  |  |  | Jason Trout | 2022-02-28 | Support justification for 900hr/PE preventative mx

## CED 11230
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Crew Entry Door | 1560-00-331-4843 | 11230 | NA | NA | Root Cause Analysis 13 Jan 22 - moved to CA/Watch List | Data Integrity | [5 empty] | Supply constraint root cause: Short/medium term fix in work: RSO/PavCon initiate RCA to identify potential short term solutions Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term):
Notes on Part from Constraints Analysis Meeting
There is no WUC separately for the torque tube for the pilot door
Team advised to select top candidates from the breakdown analysis once rerun with only 12-month data
Action Items
Action Item: PavCon to identify top candidates from 12-month breakdown analysis
Action Item: PavCon to complete eRCM analysis on any parts identified that have not yet been analyzed
Action Item: PavCon to review Mx data for WUC 11230 to see if any removals can be attributed to a five-digit WUC
Action Item: Mr. Hollenbeck to determine from where mean time between failure (MTBF) data on 1-n list is collected.
Action Item: PavCon to rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38
Notes from Parts Update Meeting 13 Jan 22
Lot of data from depot / PDM which is expected for CED
Recommend moving to Watch List - confirmed
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Identify top candidates from 12-month breakdown analysis |  |  |  | Mary Bush | COMPLETE | Most maintainers are using WUC 11230 CED for mx instead of the actual part failing and being replaced (CEDs are not typically R2). Top mx drivers include 1123C rubber diaphragm seal, 1123D latch mechanism, 11235 winch but these are minimal compared to mx actions for 11230 CED.
Complete eRCM analysis on parts identified in BA that have not yet been analyzed |  |  |  | Shawn Driscoll | COMPLETE | PavCon does not believe analysis is warranted on any subcomponents at this time
Review mx data for WUC 11230 to determine if any removals can be attributed to a 5-digit WUC |  |  |  | Neal Camren | COMPLETE
Determine from where MTBF data on 1-n list is collected |  |  |  | Dave Hollenbeck | COMPLETE | AMC pulls the MTBF data from G081 using formula in TO 00-20-2 which is (Flying Hours * QPA * Usage Factor)/MTBF-1 Inherent Failures
Rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38 |  |  |  | Shawn Driscoll, Mary Bush | COMPLETE | Breakdown analyses completed with 18-month data; profile pages generated

## Boom 46750
5 Digit WUC Description | NSN | WUC | Repair Concept | Source of Repair | Current All In Process Phase | Primary Constraint(s) | Constraint Bucket 1 | Constraint Bucket 2 | Constraint Bucket 3 | Constraint Bucket 4 | Constraint Bucket 5 | On-going IPT part improvement efforts + KC-135 Potential Actions | Component Data Collection Study | Constraint Analysis Comments | Engineering Review/ Intent/ Funding decision | Design Change Type | FFF or MOD | Funding Dollars | Budget Code | Attrition or Forced Generation | IIRP Candidate? | Next Step | IIRP 1 (6 months) Pre-Approval | IIRP 2 (1 year) Formal Package Generation and Budgeting Efforts | IIRP 3 (1 year) Procurement, Installation, and Tracking | IPT POC | Overall Timing | Est Cost | Help Needed
Boom Assembly | 001095725 001095730 | 46750 | NA | NA | Solution Implementation | Part Failure (High Break Rate) | Supply Constraints | IIRP |  |  |  | Supply constraint root cause: Short/medium term fix in work: Risks (threats): Risk Mitigation Actions Gov Council discussion (for short term): Risk Mitigation Action for Gov Council discussion (long term):
Notes on Part from Constraints Analysis Meeting
SPO is interested in the new boom assembly design used by Foreign Military Sales (FMS) aircraft; new design is lighter with less subassemblies and parts
Previous lead is no longer with the SPO, and a new point of contact is needed
The team questioned whether the new boom could be an IIRP
Action Items
Action Item: Mr. Schwartz to identify a new lead within the SPO for the FMS boom and provide All-In details to lead
Action Item: Mr. Schwartz (and new lead) to pursue potential IIRP for boom replacement.
Action Item: PavCon to rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38
Notes from Parts Update Meeting 13 Jan 22
Dewayne will follow up with Jeremy and Boom lead
Action Item |  |  |  | Responsible Party | Due Date | Notes / Status
Identify a new lead within the SPO for the FMS boom; provide All-In details to SPO boom lead |  |  |  | Jeremy Schwartz | 2022-01-31 | IPT working the boom; Dewayne will ID POC
Pursue potential IIRP for boom replacement |  |  |  | Jeremy Schwartz / New Boom Lead | OBE | Dewayne - unlikely to use IIRP; procure subcomponents are assemble at Tinker
Rerun breakdown analyses using only 12-month data for all assemblies and systems contained in Top 38 |  |  |  | Shawn Driscoll, Mary Bush | COMPLETE | Breakdown analyses completed with 18-month data; profile pages generated